## Sheet1
| Stella | [5 empty] | Wanlu | [5 empty] | Cuimin |  | Yihan
Prototyping
| Cuimin's project |  | Task status | Yihan's project |  | Task status | Cuimin's project |  | Task status | Yihan's project |  | Task status | Task | Task status | Task | Task status
Jun13-Jun20 | 1. Read deadline requirements & updated project requirement files | 2. Contact Cuimin if there's any doubts | ✓ | 1. Read deadline requirements & revise tasks if necessary | 2. Contact Yihan if there's any doubts & confirm deadline | ✓ | 1. Read deadline requirements & updated project requirement files | 2. Contact Cuimin if there's any doubts | ✓ | 1. Read deadline requirements & revise tasks if necessary | 2. Contact Yihan if there's any doubts & confirm deadline | ✓ | 1. Provide concrete deadline | ✓ | 1. Provide concrete deadline | ✓
2021-06-01 | 1. Communicate with Wanlu on how to integrate front-end and back-end code | 2. Contact Cuimin if there's any doubts | ✓ | 1. Revise stage 1 (selecting study and conditions) according to Mock-up file slide 8 | 2. Revise stage 2 according to mock-up file slide 9 | ✓ | 1. Communicate with Stella on how to integrate scripts and front-end code | 2. Contact Cuimin if there's any doubts | ✓ | 1. Organize variables and scripts (including main experiment's scripts) for each stage and for each study (scripts should correspond to conditions and studies) | 2. Communicate with Stella about what variables and attributes she need to quote | ✓ | Check previous day's work | ✓ | Check previous day's work | ✓
2022-06-01 | 1. Do up pages for survey: Q1 & Q2 (front-end) | 2. Do up pages for pilot condition (remove avatar from intro page and chatting page) |  | 1. Revise stage 3 according to mock-up file slide 10 | 2. Contact Yihan if there's any doubts |  | 1. Do up scripts library (back-end) - female, male, neutral, pilot condition | 2. Do up data storage and response validation for chat (back-end) |  | 1. Update stage 1 of the webpage http://robo-advisor-197502.appspot.com/ | 2. Update stage 2 of the webpage |  | Check previous day's work |  | Check previous day's work
2023-06-01 | 1. Do up set-up pages (front-end; to model after Yihan's Stage 1) | 2. Edit scripts (front-end) after Wanlu is done with the back-end - Female & Male condition |  | 1. Create stage 0 (slide 2, the page that asks participants to enter metric number); create final page (slide 7, thank you for participating); | 2. Create re-directing page (slide 6, you'll be directed to external portal); create manipulation check page (see PRD page 7) |  | 1. Do up data storage and response validation for survey (back-end) | 1. Do up data storage for set-up: study conditions etc. (KIV, model after Yihan's); Organize variables and scripts to correspond to conditions and studies |  | 1. Update stage 3 of the webpage | 2. Refer to PRD page 6: 1. Save the following data: trust_t0, trust_t1, commit_1~commit_n 2. Save robo-advisor’s monthly performance data accordingly 3. Create sub-libraries for each scenario category 4. Make sure that the loaded script cannot be repeated more than three times 5. Calculate bonus and save it as bonus 6. Create a dummy variable for the top 10% performers for each condition |  | Critical feedback on previous day's work |  | Critical feedback on previous day's work
2024-06-01 | 1. Edit scripts (front-end) after Wanlu is done with the back-end - Neutral condition | 1. Edit scripts (front-end) after Wanlu is done with the back-end - Pilot study conditions |  | 1. Create hyperlinks for each stage, and arrange all stages chronologically | 2. Make all pages responsive |  | 1. Upload new pages that Stella created to the webpage | 2. Contact Yihan if there's any doubts |  | 1. Upload new pages that Stella created to the webpage | 2. Contact Yihan if there's any doubts |  | Check previous day's work |  | Check previous day's work
2025-06-01 | 1. Create hyperlinks for each stage, and arrange all stages chronologically | 2. Make all pages responsive and test pages on different OS and devices for compatibility and responsiveness; test different conditions and studies to see if they match |  | 1. Test pages on different OS and devices for compatibility and responsiveness | 2. Tesk different conditions and studies to see if they are matched |  | 1. Do randomization for pilot study (KIV, model after Yihan's) | 1. Test pages on different OS and devices for compatibility and responsiveness; test different conditions and studies to see if they match |  | 1. Test pages on different OS and devices for compatibility and responsiveness | 2. Tesk different conditions and studies to see if they are matched |  | Check previous day's work |  | Check previous day's work
2026-06-01 | Work on unfinished parts of previous days |  |  | Work on unfinished parts of previous days |  |  | Work on unfinished parts of previous days |  |  | Work on unfinished parts of previous days |  |  | Overall feedback on previous days' work |  | Overall feedback on previous days' work
2027-06-01 | Finish prototype |  |  | Finish prototype |  |  | Finish prototype |  |  | Finish prototype |  |  | Overall feedback for revision |  | Overall feedback for revision
Revision
| Cuimin's project |  |  | Yihan's project |  |  | Cuimin's project |  |  | Yihan's project |  |  | Task | Task status | Task | Task status
2028-06-01 | 1. Address revision feedback | 2. To be updated |  | 1. Address revision feedback | 2. To be updated |  | 1. Address revision feedback | 2. To be updated |  | 1. Address revision feedback | 2. To be updated |  | Update revision feedback |  | Update revision feedback
2029-06-01
2030-06-01 | 1. Finish reivision |  |  | 1. Claim payment |  |  | 1. Finish revision |  |  | 1. Claim payment